## Start here
Project cost and profitability tracker
Free edition from MIYAR Business Tools · https://miyarbusiness.com
What does this file answer?
Is your project still profitable? This file compares the budget of each cost line with its actual cost and progress, estimates the final cost, and shows the expected profit and margin at completion before you reach the final account.
How to use
1. Open the “Cost” sheet and enter the contract value and project name.
2. For each cost line enter the budget, actual cost to date and physical progress of that line.
3. The file calculates earned value, estimate at completion and variance for each line.
4. Read the result panel below the table: expected profit, margin, cost performance index and verdict.
Colour guide
Input cell | Yellow background, blue text: type here.
Calculated cell | White background: a formula, do not type over it.
Notes
• Progress means the physical progress of the line, not the share of its budget already spent.
• The estimate at completion assumes each line keeps its current performance to the end. A line that has not started is counted at its budget.
• Capacity: one project and 8 cost lines. The full MK-02 tool tracks several projects month by month, including variation orders.

## Cost
Project cost and profitability
Yellow cells are for input; white cells are calculated. The current figures are an example: replace them with your project data.
Project name | Water pipeline — Ahmadi
Contract value incl. approved variations (KWD) | 1200000
Report date | 2026-10-05
Cost line | Budget (KWD) | Actual cost to date (KWD) | Line progress | Earned value (KWD) | Estimate at completion (KWD) | Expected variance (KWD) | Cost performance index
Materials | 450000 | 236000 | 55% | 247500 | 429090.9091 | 20909.0909 | 1.0487
Labour | 300000 | 171000 | 52% | 156000 | 328846.1538 | -28846.1538 | 0.91228
Equipment | 120000 | 58500 | 50% | 60000 | 117000 | 3000 | 1.0256
Subcontractors | 160000 | 54000 | 30% | 48000 | 180000 | -20000 | 0.88889
Site overheads | 60000 | 33500 | 50% | 30000 | 67000 | -7000 | 0.89552
Transport and storage | 25000 | 14200 | 50% | 12500 | 28400 | -3400 | 0.88028
Insurance and guarantees | 20000 | 12000 | 60% | 12000 | 20000 | 0 | 1
Other | 15000 | 2500 | 10% | 1500 | 25000 | -10000 | 0.6
Total | 1150000 | 581700 | 49.35% | 567500 | 1195337.0629 | -45337.0629 | 0.97559
Result | Value
Total cost budget (KWD) | 1150000
Estimate at completion (KWD) | 1195337.0629
Planned profit at pricing (KWD) | 50000
Expected profit at completion (KWD) | 4662.9371
Planned margin | 4.167%
Expected margin | 0.3886%
Project cost performance index | 0.97559
Verdict | Needs attention

## Full version
What does the full version add? MK-02
This free edition is fully functional within its limits. When your workload grows, move to the full version.
Feature | Free edition | Full version
Budget against actual for every line | ✓ | ✓
Estimate at completion and expected profit | ✓ | ✓
Number of projects | One project | Multiple projects
Number of cost lines | 8 | Detailed lines, no practical limit
Monthly tracking and variance trend over time | — | ✓
Variation orders and their effect on contract and cost | — | ✓
Link between cost, certificates and collections | — | ✓
Dashboard and charts | — | ✓
Product page: https://miyarbusiness.com/product/mk-02-project-cost-profitability/